## Sheet1
Those Meddling Kids Gantt Chart
Task / Catagory | Task Assignee | Memo | Week1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6
|  |  | M - 10/23 | T - 10/24 | W - 10/25 | R - 10/26 | F - 10/27 | S - 10/28 | S - 10/29 | M - 10/30 | T - 10/31 | W - 11/1 | R - 11/2 | F - 11/3 | S - 11/4 | S - 11/5 | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S
Full Stack
Brainstorm Project Ideas | All
Select Project Idea | All | Completed 10/25
Determine Framework | Pat | Completed 10/25
Set up repository and get things rolling | Pat | Completed 10/25
Add Routing to Documentation Generated by Doxygen | Pat | TBD (Proj3)
Validate Prototype Functionality Via Manual Testing | Pat | TBD (Proj3)
Determine Test Suite Methodology | TBD | TBD
Add Baseline Scraper Test | TBD | TBD
Modify search to handle a list of requests | Pat | TBD
Validate Iteration (Each Week) | Pat | TBD
Integrate High-Low Results Toggler with result View | Pat | TBD
Integrate number of results requested into view | Pat | TBD
Create New tests for new scraper functions | Ellis | TBD
Look into using Machine Learning to Improve result quality | Pat | TBD
Add "Get Directions" link for a given search result | All | TBD
Backend
Develop Baseline Web Scraper Functionality | Ellis | Completed
Determine Format that Scraper Returns | Ellis | Completed
Integrate Other Services Into Scraper | Ellis | Services TBD
Parse Other Services into Usable Data | Ellis | TBD
Rank Data Accordingly | Ellis | TBD
Add functionality to return highest and lowest results | Ellis | TBD
Frontend
Create Routing Between Home, Search, and Results pages | Pat | Completed 10/28
Look Into Posting Results from Python Function Into a View | Liam | TBD (Proj3)
Combine Scraper Output and Results From Above | Liam | TBD (Proj3)
CSS/Make Pretty | Liam | TBD (Proj3)
Reactify? | Pat/Liam | TBD
Integrate Form Addition/Subtraction of Options in Search View | Liam | TBD
Look into deployment | Pat | TBD
High/Low Results Toggler | Liam | TBD
Option to select number of top results to return | Liam | TBD
Documentation
Continually Update the Gantt Chart | All | Ongoing Process
Figure out Doxygen and Use with Python | Pat | Completed 10/30
Update ReadMe with any New Package Information | All | Ongoing
Review And Update Tasks | Pat | Ongoing(Each Monday)
Create & Update Use Case Diagram | Pat | TBD
Review Requirements and Validate that all are met | Pat
Create & Update Class Diagram
Create & Update State Diagram
Create & Update Product Backlog | Pat | Recurrant(Completed 11/1)
Create & Update Sprint Backlog | Pat | Recurrant(Completed 11/1)
Reach Goals
DB for Search Results
ML for Improving Suggestions